## Asset List
Task | Filename | Assigned To | Date Assigned | Alpha | Beta | Complete Yes/No | Notes | Trello: | https://trello.com/b/1qTsyE8Q/space-invaders-group-project
Octopus (Large Invader) Sprite | Octopus.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Crab (Medium Invader) Sprite | Crab.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Squid (Small Invader) Sprite | Squid.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Enemy Death Sprite | Destroyed.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | No
Player Sprite | LaserCanon.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Player Death Sprite | LaserCanonDestroyed.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Shield | Shield.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Shield Erosion Left | UnderArchLeft.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Shield Erosion Right | UnderArchRight.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Shield Block Erosion | ShieldBlock.png | Adithi | 2019-02-19 | 2019-02-20 | 2019-02-27 | Yes
Squiggle Laser | SquiggleLaser.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Cross Laser | CrossLaser.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Laser | Laser.png | Adithi | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Player Death Sound | PlayerDeath.wav | Tea | 2019-02-19 | 2019-02-27 | 2019-02-27 | No
Shooting Sound | Shooting.wav | Tea | 2019-02-19 | 2019-02-27 | 2019-02-27 | No
UFO Sound | UFO.wav | Tea | 2019-02-19 | 2019-02-27 | 2019-02-27 | No
UFO Death Sound | UFODeath.wav | Tea | 2019-02-19 | 2019-02-27 | 2019-02-27 | No
Enemy Death Sound | EnemyDeath.wav | Tea | 2019-02-19 | 2019-02-27 | 2019-02-27 | No
Background Music | Background.wav | Tea | 2019-02-20 | 2019-02-27 | 2019-02-27 | No
Player movement | PlayerMovement.zilchscript | Blake | 2019-02-21 | 2019-02-21 | 2019-02-27 | Yes
Score | Score.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | No
Player shooting script | PlayerShoot.zilchscript | Blake | 2019-02-22 | 2019-02-22 | 2019-02-27 | Yes
Health | Health.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
Main menu buttons | StartButton.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
In Game buttons | NewGameButton.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
Win condition | NextWave.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
Lose condition | PlayerLose.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
Loss message | LossMessage.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | Yes
Enemy Movement Client | EnemyMovement_Client.zilchscript | Blake | 2019-02-22 | 2019-02-27 | 2019-02-27 | No | Includes Enemy Fire
Enemy Movement Server | EnemyMovement_Server.zilchscript | Blake | 2019-02-22 | 2019-02-27 | 2019-02-27 | No | Includes Enemy Fire
PlayerLives | PlayerLives.zilchscript | Blake | 2019-02-25 | 2019-02-25 | 2019-02-27 | In Progress
Start Screen Animation | StartScreenAnimation.png | Blake | 2019-02-19 | 2019-02-19 | 2019-02-27 | Yes
Variables
PlayerSpeed | Adjusts the speed of the player
EnemySpeed | Adjusts the speed of the enemies
BulletSpeed | Adjusts the speed of the Bullets
ReloadTime | Adjusts the amount of time it takes the enemies to reload